## Sheet1
ID	DESCRIPTION	HOW TO REPLAY	TYPE	SEVERITY	COMMENT	STATUS
1	on map view rotation the map rotates in the other direction when it comes to 360	BrowseMap menu, select map rotate	bug	minor	there’s something to fix in MapViewerControlObj::MoveMap	opened
2	automatically moves the map when button keeps pushing	BrowseMap menu, select map move	improvement	trivial		opened
3	no position shown on map view (without guidance and positioning), no address	First start when map is displayed	bug	minor	maybe a way to fix is to implement setposition ?	opened
4	vehicle oriented to destination doesn’t make sense if no guidance active	BrowseMap menu, select map direction	bug	minor		opened
5	MAP menu empty	in settings goto MAP menu	missing	trivial		opened
6	search on category not active	in POI menu, enter a character when search for a category	bug	minor		opened
7	area to show maneuver list on browse map is bigger that the destination flag	the pop-up is launched even if push on guidance area	bug	trivial	HMI in qml, maybe gimp file ?
8	improve the list of maneuvers	in browse map when guidance is active, push on destination flag	improvement	trivial		opened
9	next maneuver to show on map pip	in POI or in search menu, when a guidance is active	missing	minor		opened
10	reroute on fuel low doesn’t run correctly	in browse map, push on cannister	bug	major		opened
11	delete route fails on quit	seen in debug mode ([INFO ][FSAC] DeleteRoute / argument list must have even number of elements, not 5)	bug	major	remove the deleteroute in App, because it doesn’t need to tp managed there	fixed
12	if no route calculated, no access to route settings	cost model and routing preferences need a valid route handle	bug	major	NB: when does it make sense to create a route handle ?	fixed
13	geolocation of the maneuver is missing, it’d be helpful to allow to navigate from maneuver to maneuver	needed by ID8	missing	minor		opened
14
BUG LIST TO REMIND FIX HISTORY